## Sheet1
Feature_ID | Feature_Name | Team | Planned_Sprint | Actual_Sprint | Status | Story_Points | Milestone | Risk_Flag | Dependency_Team
F01 | Login Refactor | Team Alpha | Sprint 4 | Sprint 5 | Done | 13 | Alpha Release | Low
F02 | API Gateway Setup | Team Bravo | Sprint 4 | null | In Progress | 21 | Alpha Release | High | Team Alpha
F03 | Payment Integration | Team Delta | Sprint 5 | null | Planned | 34 | Beta Release | Medium | Team Bravo
F04 | User Analytics | Team Alpha | Sprint 6 | Sprint 6 | Done | 20 | Beta Release | Low
F05 | Notification Module | Team Bravo | Sprint 5 | null | In Progress | 16 | Beta Release | High
F06 | Auth Token Refresh | Team Delta | Sprint 4 | Sprint 5 | Done | 18 | Alpha Release | Low | Team Alpha
F07 | Email Verification | Team Alpha | Sprint 5 | Sprint 6 | Done | 8 | Beta Release | Low
F08 | Performance Audit | Team Bravo | Sprint 6 | null | Planned | 22 | Go Live | Medium | Team Delta
F09 | Security Hardening | Team Delta | Sprint 6 | null | In Progress | 29 | Go Live | High | Team Bravo
F10 | UI Final Polish | Team Alpha | Sprint 6 | null | Planned | 12 | Go Live | Medium